## Issue Tracking Log
http://bit.ly/2VO7t67
| PROJECT | Comprehensive Assessment and Preparation System (Mobile)
| START DATE | 03/22/2026 (WEEK %)
DATE | LOGGED BY (NAME OF USER) | DESCRIPTION | POSITION | ISSUE TYPE | SUGGESTION / COMMENTS | STATUS | PRIORITY
03/27/2026 | Lejanie Embrado | Notification alerts not accurate. Even for this role, there's an allert that says about taking quiz when this role can't atke quizzes. Only students can't. | ASSOCIATE DEAN | BUGS | Review notification requirements | PENDING | HIGH
03/27/2026 | Testtt teerrr Ter | The dashboard already has a data even if I used a new account and haven't attempted any quiz yet. | STUDENT | BUGS | Make sure a single data isn't applied to every student role. | PENDING | HIGH
03/27/2026 | Testtt teerrr Ter | I've changed my name as a test and added a 2nd first name, it actually came out as a last name on my Profile. | STUDENT | BUGS | Allocate a strict first name field where it accepts 2-3 worded names. | PENDING | MEDIUM
03/27/2026 | Testtt teerrr Ter | Some text appear as white like it's been highlighted. The text are not supported. | STUDENT | BUGS | Check the text styling requirements. | PENDING | HIGH
03/27/2026 | Testtt teerrr Ter | Broken links of images appear in question section when taking quiz. | STUDENT | BUGS | Make sure to link images properly. | PENDING | HIGH
03/27/2026 | Testtt teerrr Ter | After successfully submitting a quiz, the data aren't updated and stays the same. | STUDENT | BUGS | Make data is updated accurately. | PENDING | HIGH
03/27/2026 | Testtt teerrr Ter | Leaderboard data can't be fetched. | STUDENT | ERROR | Make sure backend is connected to frontend. | PENDING | HIGH
03/27/2026 | Testtt teerrr Ter | Google Authentication error. | STUDENT | ERROR | Make sure to provide correct URI for Google Authentication. | PENDING | HIGH
03/27/2026 | Testtt teerrr Ter | Facebook Authentication error. | STUDENT | ERROR | Make sure to provide correct URI for Facebook Authentication. | PENDING | HIGH
03/27/2026 | Testtt teerrr Ter | "Mark all as read" notification feature not working properly. | STUDENT | BUGS | Make sure toreally mark it as read and remove the red alert after that. | PENDING | HIGH