## Issue Tracking Log
| PROJECT | Comprehensive Assessment and Preparation System (Mobile)
| START DATE | 03/16/2026
DATE | LOGGED BY (NAME OF USER) | DESCRIPTION | POSITION | ISSUE TYPE | SUGGESTION / COMMENTS | STATUS | PRIORITY
03/20/2026 | Dean Account | When adding a quiz in Dark Mode using the "+" button and adding the Quiz Name field, the entered name can't be seen as the text color seems to blend with the white background. | DEAN | BUGS | Change font color to black. | PENDING | LOW
03/20/2026 | Dean Account | Upon adding a Quiz's Basic Information, when the user didn't enter anything in the required field, it didn’t display any suggestion or invalid warning. | DEAN | ENHANCEMENTS | Invalid Input or Warning messages needed. | PENDING | LOW
03/20/2026 | CPE Student | The Bottom Navigation Bar where "Home" and "Leaderboard" is stored has a white-like border even in darkmode. It seems like the white color of the Tab Bar (for light mode) and the black color (for the dark mode) are overlapping. | STUDENT | ENHANCEMENTS | Enhance the Tab Bar for both display mode. | PENDING | LOW
03/20/2026 | CPE Student | On the Register Account screen, the Select Campus dropdown when opened overlaps and fully covers the input fields below it (z-index layering bug), preventing the user from seeing or interacting with the obscured fields. | STUDENT | BUGS | Fix dropdown z-index/overlay rendering so the expanded list does not cover sibling form fields. | PENDING | HIGH
03/20/2026 | CPE Student | On the Register Account screen, placeholder text in some input fields is rendered in a color that blends with the field background (white or near-white text on white background), making field labels unreadable without focus. | STUDENT | BUGS | Change placeholder text color to a contrasting shade (e.g., gray) that is visible against the field background in both light and dark modes. | PENDING | MEDIUM
03/20/2026 | CPE Student | The Server Config option is accessible from the user profile menu for regular Student accounts. This exposes server endpoint configuration to non-admin users, which is a security and UX concern. | STUDENT | BUGS | Restrict the Server Config menu item to administrator or developer roles only. Hide it from standard Student and Dean accounts. | PENDING | HIGH
03/20/2026 | CPE Student | The Available Subjects section on the Home screen shows "No subjects available" for the test Student account even after login, with no loading indicator or explanation distinguishing between no data and a failed data fetch. | STUDENT | ENHANCEMENTS | Add a loading state and differentiate empty-state messages (e.g., "No subjects enrolled" vs "Failed to load subjects") to improve user clarity. | PENDING | LOW