## UI Test Result
Role | Test Case | Campus | Test Data | Status | Explanation | Error Code | Indicator | Interpretation
PUBLIC | Forgot Password |  |  |  | 1. No Email received. |  |  | OK
| Reset Password | [6 empty] | BUGS (INCOMPLETE)
| Login Validation | [6 empty] | NEEDS ENHANCEMENT
| Register Navigation |  |  |  | 1. The User Code field accepts random string, not the desired User Code fromat. |  |  | ERROR
[5 empty] | 2. Campus field choices not named correctly. This will lead to confusion. |  |  | NOT FOUND/MISSING
Register Step 1
Register Step 2
Register Step 3
Register Step 4
Register Submit
Dark Mode and Light Mode Feature
| Team Caps Navigation |  |  |  | 1. Unclickable. | 500
| Facebook Auth |  |  |  | 1. Facebook Client ID is missing. Check your .env file and configuration cache.
Google Auth
Remember Me
Biometric Prompt
Biometric Login
DEAN | Dashboard Navigation | MAIN | ID: 23-A-12345
Navigation Buttons
View/manage users in dashboard
| Admin and Students Count |  |  |  | 1. Number of Admins and Students are incorrect.
User Approval
User Deactivation
User Change Role
Profile Management
Admin Tools
Subject Management
Subject Search
Leaderboards
Enhancemeny & Analytics
- Overview
1. Number of Students
2. Average Score
3. Pass Rate
4. Improvement
5. Trend Snapshot
6. Pass vs Fail
7. Program Performance
- Students
Analytics
| 1. Content Summary |  |  |  | 1. Content Summary "Most Viewed Lessons", "Most Attempted Questions" not displaying
acurate data.
2. Top Subjects
3. Weakest Topics
4. Recent Progress
Insights Hub (Accessed Via Admin Tools in Dashboard)
1. Analytics Overview
2. Student Enhancement
| 3. Reports Hub |  |  |  | 1. Should not be in a separate place, a more accessible one.
| a. Recent Takers |  |  |  | 1. Score show is incorrect and should only display highest score.
b. Leaderboard
c. All Reports
4. Support Queue
5. Export & Print
Subject Question Management
| Duplicate Questions |  |  |  | Failed to load question data.
List of Questions
Add Subject (Admin Tools)
| Add Question |  |  |  | Added question not found but was added to question count.
Delete Question
Print / Export
Announcement
Notification
| Clicking "Mark all as read" |  |  |  | 1. Won't mark questions as "Read" as unreadCount is unpopulated from the /api/notifications API.
Support
Viewing Support Tickets
Dark Mode and Light Mode Feature
User Search and Filter
| Duplicate Question |  |  |  | 1. Failed to load question data.
| Class Navigation |  |  |  | 1, Used routes should be reviewed and timely data needs to be improved without refereshing.
| Class Oversight |  |  |  | 1. Class Instructor should be shown.
Archived Classes
Add Class
Bulk User Actions
Bulk Approve Users
| Log-Out |  |  |  | The "Cancel" text is not that visible. It blended with the background.
ASSOCIATE DEAN TESTING | Dashboard Navigation | MAIN | ID: 23-A-22220
| Number of "Students", "Faculty", "Programs", and "Subjects" |  |  |  | 1. Numbers are incorrect.
College Performance
Quick Actions
| a. Subject Oversight |  |  |  | 1. Incorrect route used. Will lead you to "Reports Hub".
b. Classes
c. User Management
| d. Analytics |  |  |  | 1. Incorrect route used. Will lead to "Subjects".
| Program Comparison |  |  |  | 1. Hardcoded data used, not real ones.
| Subject Oversight |  |  |  | 1. The Subjects screen stays in loading mode because it's waiting for a response from the backend
API (/api/subjects), but the API server isn't running or isn't reachable from the device, so the
request never finishes to hide the loading indicator.
Navigation Buttons
View/manage users in dashboard
| Admin and Students Count |  |  |  | 1. Number of Admins and Students are incorrect.
User Approval
User Deactivation
User Change Role
Profile Management
Subject Question Management
| List of Questions |  |  |  | 1. The Subjects screen stays in loading mode because it's waiting for a response from the backend
| Add Subject |  |  |  | API (/api/subjects), but the API server isn't running or isn't reachable from the device, so the
| Add Question |  |  |  | request never finishes to hide the loading indicator.
Delete Question
Print / Export
Enhancemeny & Analytics
- Overview
| 1. Number of Students |  |  |  | 1. Incorrect number/count of students.
2. Average Score
3. Pass Rate
4. Improvement
5. Trend Snapshot
6. Pass vs Fail
7. Program Performance
- Students
| - Analytics |  |  |  | 1. Content Summary "Most Viewed Lessons", "Most Attempted Questions" not displaying
acurate data.
Notification
| Clicking "Mark all as read" |  |  |  | 1. Won't mark questions as "Read" as unreadCount is unpopulated from the /api/notifications API.
Insights Hub (Accessed Via Admin Tools in Dashboard)
1. Analytics Overview
2. Student Enhancement
| 3. Reports Hub |  |  |  | 1. Should not be in a separate place, a more accessible one.
| a. Recent Takers |  |  |  | 1. Score show is incorrect and should only display highest score.
| b. Leaderboard |  |  |  | No filter options.
c. All Reports
4. Export & Print
5. Classes
Dark Mode and Light Mode Feature
Create Announcement
| Class Navigation |  |  |  | 1, Used routes should be reviewed and timely data needs to be improved without refereshing.
| Class Oversight |  |  |  | 1. Class Instructor should be shown.
Archived Classes
Add Class
Students List
| Asign Quiz |  |  |  | 1. No Avaliable Quiz (Subject) appearing for Assigning Quiz.
Bulk User Actions
Bulk Approve Users
Bulk Activate Users
Bulk Deactivate Users
Log-Out
INSTRUCTOR TESTING | Faculty Dashboard Navigation | MAIN | ID: 23-A-12347
| Number of "Students" (Clickable) |  |  |  | 1. Number of Students are incorrect.
| Number of "Subjects" (Clickable) |  |  |  | 1. Should only show the number of Faculty's own subject, not all of the subject in the system.
| Number of"Quizzes" (Clickable) |  |  |  | 1. Actually shows the number of questions of the Faculty's Subjects.
Navigation Buttons
Subject Question Management
| List of Questions |  |  |  | 1. Faculty questions API endpoint not returning data, consult Backend Developer.
Add Question
Delete Question
Print / Export
| Create Quiz |  |  |  | 1. Creates or adds a question, not a quiz.
Class Average
Notification
| Clicking "Mark all as read" |  |  |  | 1. Won't mark questions as "Read" as unreadCount is unpopulated from the /api/notifications API.
Insights Hub (Accessed Via Admin Tools in Dashboard)
| 1. Reports Hub |  |  |  | 1. Should not be in a separate place, a more accessible one.
| a. Recent Takers |  |  |  | 1. Score show is incorrect and should only display highest score.
| b. Leaderboard |  |  |  | 1. No filter options.
c. All Reports
2. My Classes
3. My Subjects
4. Create Quiz
Reports
View Recent Takers
| Leaderboards |  |  |  | No filter options.
| All reports (This is actually Support Tickets) |  |  | !!! | Shold be removed and not be available in this role even if it shows empty reports.
Class Navigation
| Class Oversight |  |  |  | Needs to be refreshed to show updates or changes in Class Oversight
Archived Classes
Add Class
Students List
| Asign Quiz |  |  |  | 1. No Avaliable Quiz (Subject) appearing for Assigning Quiz.
Profile Management
Dark Mode and Light Mode Feature
Log-Out
PROGRAM CHAIR TESTING | Dashboard Navigation | MAIN | ID: 23-A-12346
1. Number of "Students" (Clickable)
| 2. Number of "Faculty" (Clickable) |  |  |  | 1. Numbers are incorrect.
| 3. Number of"Quizzes" (Clickable) |  |  |  | 1. Actually shows the number of questions of the Subjects.
4. Number of"Subjects" (Clickable)
- Program Performance
- Quick Actions
| 1. Manage Subjects |  |  |  | 1. Labeled as "Manage Subjects" but takes you to "Reports Hub". Misleading label.
| 2. User Management |  |  |  | 1. Number of "Admins" and "Students" are incorrect.
3. Manage Classes
| 4. Generate Reports |  |  |  | 1. Leads to "Program Subjects". Misleading label.
Subject Overview
Navigation Buttons
Subject Question Management
| List of Questions |  |  |  | 1. Says it's pending but it's already on the student's exam questions and not on "Pending" section.
Add Question (Admin Tools)
Delete Question
Print / Export (Admin Tools)
Class Navigation
| Class Oversight |  |  |  | Needs to be refreshed to show updates or changes in Class Oversight
Archived Classes
| Add Class |  |  |  | Input fields shifts up, making it hard to see inputted values.
Students List
| Asign Quiz |  |  |  | 1. No Avaliable Quiz (Subject) appearing for Assigning Quiz.
Notification
| Clicking "Mark all as read" |  |  |  | 1. Won't mark questions as "Read" as unreadCount is unpopulated from the /api/notifications API.
Create Announcement
Dark Mode and Light Mode Feature
Profile Management
Log-Out
STUDENT TESTING |  | MAIN | ID: 24-A-00236
| Navigation Buttons |  |  |  | 1. Still not adjusted, covered by Phone's Navigation Buttons.
| Live Exam |  |  |  | 2. Subject listed are repititive as if duplicated.
Take assigned quizzes
View quiz results after completion
View quiz attempt history
| Analytics |  |  |  | No time data available for the "Time per Topic" analytics report.
Profile Management
Notifications
| Clicking "Mark all as read" |  |  |  | 1. Won't mark questions as "Read" as unreadCount is unpopulated from the /api/notifications API.
Help Center (FAQS)
Help Center (Submitting Support Tickets)
Practice Exam Timer
Classes
| Join Class |  |  |  | 1. Input filed can't be seen as covered by keyboard when typing.
| Class Quizzes |  |  |  | Cannot be determined as there's no assigned quizzes to this class ye due to a bug.
Class History (Quiz History)
Leaderboard
| Leaderboard showing highest average scores and highest individual scores |  |  |  | Average scores not shown
| Leaderboard showing highest average scores and highest individual scores (weekly) |  |  |  | Points are only assigned.
| Leaderboard showing highest average scores and highest individual scores (when filtered) |  |  |  | 1. No data shown even though multiple users have data for multiple subject.
Student Insights
| Time per Topic |  |  |  | No data but user already taken a lot of practice exams.
Weak Areas
Strong Areas
Frequently Mistaken
Recent Performance / Practice History
Exams Taken
Average Score
Best Score
Tries to Pass
| Improving/Declining Remarks |  |  |  | Reevaluate basis for this. It seems like the logic for this is reversed.
Practice Exam Results
Take Practice Exam
Practice Exam Info
My Bookmarks
Log-Out